## Product backlog
TanyaJava.com
Klonengan stackoverflow.com
Sprint dilakukan dalam satuan 4 minggu
ID | Description | Sprint # | 1 | 2 | 3 | 4 | 5 | 6
|  | Effort needed for Release 1 as in the beginning of the sprint | 94 | 63 | 27 | 0 | 0 | 0
1 | Setup svn, issue tracker, scrum board, google app engine |  | 3 | 0 | 0 | 0 | 0 | 0
2 | Buat kerangka project: Spring 3.0, freemarker, Hibernate |  | 5 | 0 | 0 | 0 | 0 | 0
3 | Tampilkan pertanyaan dan jawaban dalam satu halaman |  | 13 | 0 | 0 | 0 | 0 | 0
4 | Halaman login sederhana |  | 3 | 0 | 0 | 0 | 0 | 0
5 | voting untuk pertanyaan dan jawaban |  | 13 | 0 | 0 | 0 | 0 | 0
Sprint 1 | buat kerangka project
6 | Badge untuk user |  | 10 | 0 | 0 | 0 | 0 | 0
16 | tambahkan kategori untuk pertanyaan |  | 4 | 13 | 0 | 0 | 0 | 0
17 | tambahkan tag untuk pertanyaan |  | 4 | 8 | 0 | 0 | 0 | 0
7 | full text search dengan hibernate search |  | 8 | 8 | 0 | 0 | 0 | 0
8 | halaman registrasi user baru, buat seminimal mungkin |  | 2 | 2 | 0 | 0 | 0 | 0
9 | edit profile user |  | 5 | 5 | 0 | 0 | 0 | 0
Sprint 2 | working version dimana user lain bisa bergabung
10 | daftar user dari open id |  | 10 | 13 | 13 | 0 | 0 | 0
11 | email notifikasi agar user dapat mentrack pertanyaan dan jawaban |  | 4 | 4 | 4 | 0 | 0 | 0
12 | tambahkan markdown / wiki untuk formating (Spike, riset bukan effort sebenarnya) |  | 5 | 5 | 5 | 0 | 0 | 0
13 | parsing sebagian kode agar ada pewarnaan (Spike, riset bukan effort sebenarnya) |  | 5 | 5 | 5 | 0 | 0 | 0
Sprint 3 | versi sudah cukup layak dideploy untuk beta testing
Release 1 | versi public beta
14 | api untuk akses semua aspek di aplikasi dengan json dan restfull url |  | 20 | 20 | 20 | 20 | 20 | 20
15 | cms untuk iklan sederhana (banner) |  | 20 | 20 | 20 | 20 | 20 | 20
18 | Search engine optimization (search engine is user interface) |  | 40 | 40 | 40 | 40 | 40 | 40
Sprint 4 | siap untuk release dan dipromosikan
Release 2 | Ad-supported version
| Effort in the whole backlog |  | 174 | 143 | 107 | 80 | 80 | 80
http://agilesoftwaredevelopment.com/scrum/simple-product-backlog
Note on E5: Effort as in the beginning of sprint 2
Note on D11: It is important to see how much effort was done during each sprint (team velocity). However, it would complicate the simplest formulae used here. So, for the simplest backlog it might be easier to calculate velocity manually.
Note on D13: This product backlog item was added to the product backlog after the first sprint. Therefore no estimation during sprint 1
Note on B19: In a real product backlog, items are more likely to be in the form of user stories. E.g. this item could be stated as "As a user I want to see the real weather data so that I could know what to wear before leaving home"
Note on D19: Team was so uncertain about this item during sprint one, that the estimated size was a complete question mark. Some experiments were carried out during sprint one in order to get a handle on the size
Note on E20: Note formulae. It is convenient to have values copied automatically until there is a reason to change the estimation
Note on A34: See for reference and comments. Feel free to remove the link. Though it would be very kind of you to leave it present somewhere on the sheet